## Лист1
| Link - Orchestarion | For now just route code - later LlamaIndex or LangChain |  |  |  |  | Student
| Brain LLM | Cloud LLM Groq |  |  |  |  | Academic
| Vector DB | ChromaDB ? |  |  | database indexing |  | Admin
| Data Extraction | Open source python libraries | to read documents | pypdf library
| evaluation | Open-source frameworks to judge and test the system | Ragas
| UI | Flask - html
Academic
1 | Data Gathering and Parsing | Download University Regulation documents |  |  |  | Core RAG Concept
|  | Write Python scripts and code to clean text and split documents logically. |  |  |  | Lewis, P., et al. (2020). Retrieval-Augmented Generation for Knowledge-Intensive NLP Tasks.
2 | Core Backend and Vector DB | Set up ChromaDB or pgvector. |  |  |  | Advances in Neural Information Processing Systems (NeurIPS).
Embed the text chunks and store them.
|  | Implement hybrid search (semantic + keyword). |  |  |  | Document extraction and domain specific legal RAG
3 | LLM Integration (probably Ollama) | Connect the database retrieval to a local Llama 3 model.
Prompt engineer the system to only answer if it finds a citation.
4 | Evaluation, API | Use RAGAS to quantitatively test accuracy. |  |  |  | Mitigating and proving hallucination reduction
|  | Build the Flask REST API and HTML template | Javascript | Jinja2
5 | Write-up and tests | Still pending
How to mathematically evaluate system
| Deleting file from Databases | Find and Delete updated or obsolete files from Vector Database and actual Upload folder
| challenges | The 256-Token "Blind Spot" (Embedding Model Truncation)
Because the platform relies entirely on ChromaDB’s DefaultEmbeddingFunction (all-MiniLM-L6-v2), it has a strict input ceiling of 256 tokens per chunk (roughly 150-200 words).
Lack of True Lexical Search (Pure Semantic Bias)
System operates as a 100% Dense Vector Semantic Search System. It does not feature a hybrid search layout
Absence of Chat Conversational Memory
The system does not pass historical chat transcripts back to the Groq Cloud API during a session. While database saves past messages for display on the screen, Groq treats every single submission as a blank slate
faced an issue where chat assistant provided correct text answers, but the source citations layout appeared blank until manually reloaded the browser tab.